## Slide 1: GENAI & Project-Based Learning

## Slide 2: Background
In traditional .NET courses, students with different backgrounds and learning speeds are taught using the same static curriculum.
This often results in gaps in comprehension for slow learners and a lack of challenges for advanced students.
With the integration of Generative AI, we now have the opportunity to build an AI Agent that can adaptively support and personalize the learning journey for each student.

## Slide 3: Workflow
To design and implement an AI-powered learning agent that supports students in a .NET course by providing:
Student logs in and is assigned a default learning path
Student interacts with AI Agent via chat or code editor extension
AI tracks student progress, identifies difficulties
Based on performance, AI recommends review content, new challenges, or support prompts
Student gets weekly AI-generated feedback + roadmap

## Slide 4: Why Use GenAI in PBL?
Boosts productivity and learning speed
Enhances creativity and experimentation
Simulates industry-level AI-integrated workflows
Promotes self-directed problem-solving

## Slide 5: Project-Based Learning (PBL)
Teamwork:
  3 to 5 students per group
Project Requirement:
  Choose a real-world application idea
  Use .NET Core, WPF, EF Core
  Integrate at least 1 AI feature
  Implement GitHub CI/CD pipeline
Notes: Chatbot, Personalized Recommendation, Image Recognition & Analysis, Speech-to-Text & Text-to-Speech, Fraud Detection, Predictive Analytics, Sentiment Analysis, AI-Assisted Coding

## Slide 6: Timeline & Milestones:
Phase | Weeks | Focus | Activities | Deliverables | Points
Initiation | 1–2 | Team formation & topic proposal | PBL introduction, CLO briefing, GitHub setup | Report 1 | 20%
Design | 3–4 | System analysis & architectural design | UML, DB design, UI mockups, planning CI/CD | Report 2 | 20%
Development | 5–8 | Core feature development | OOP, EF Core, WPF, multithreading | Report 3 | 20%
Integration | 9–10 | AI + CI/CD + Testing | Add GenAI features, automate builds/tests | Report 4 | 20%
Closure | 11 | Final presentation & reflection | Presentation, team/self-evaluation | Final | 20%

## Slide 7: Week 1-2: Form Teams & Propose Project Topic
Tasks
Students self-organize into teams of 3–5 members and register via a form.
Propose a software project idea including:
  Project title and the real-world problem it addresses
  Technologies to be used (must include .NET Core, WPF, and EF Core)
  At least one feature using Generative AI
  CI/CD integration (using GitHub Actions)
Deliverables
Proposal File (.pdf): Project description.
GitHub Repository Link: Initialized with branch structure based on team roles

## Slide 8: Week 3-4: System Design & Architecture
Tasks
Analyze and design the system architecture, UI flow, and database schema.
UML Design: Use Case Diagram, Class Diagram
Entity-Relationship Diagram→ Defines database tables and relationships for EF Core.
UI/UX design showing how users interact with the system.
MVVM Pattern via repository pattern for data access→ Ensures scalable, maintainable software with clear separation of concerns.
Deliverables
Architecture presentation slides (include Use Case diagram)
GitHub repo containing design files
Demo UI version (with mock data)

## Slide 9: Week 5-8: Development, CI/CD, GenAI Integration
Tasks
Implement the core application features:
OOP, Generic, Event, LINQ, WPF (CLO2, CLO3)
Database access using EF Core (CLO4)
Multithreading, Stream I/O (CLO5)
Integrate GenAI: code suggestions, test generation, documentation, data generation (CLO6)
Set up GitHub Actions to automate testing and building.
Deliverables
Full GitHub repository with CI/CD pipeline
Feature demonstration video
Progress slides

## Slide 10: Week 9-11: Final Demo & Report
Tasks
Present product.
Submit final documentation
  Presentation slides.
  Team project report.
  Individual and group self-assessment.
Deliverables
Slides + report + GitHub repository
Demo

## Slide 11: Suggested Support Tools
Team Communication: Zalo Group, Discord
Progress Management: GitHub Projects, Trello
Reports & Forms: Google Slides, Google Form
Automation: GitHub Actions
Code Review: GitHub Pull Request

## Slide 12: GitHub Project Board Template
To create this: Go to your repository → Click Projects → New Project → Choose Board view or Table.
Column Name | Description | Example Tasks
To Do | All assigned tasks that haven’t started yet | Design Use Case diagram, Set up EF Core
In Progress | Tasks currently being worked on | Build WPF User Management UI, Integrate AI-based test generation
Testing | Completed features under internal testing | Test Stream I/O, Verify GitHub CI/CD workflow
Done | Tasks completed and accepted | Implement database schema, Push Login/Signup features
Blocked / Discussion | Tasks needing support or discussion | UI binding issue, CI pipeline not running

## Slide 13: Checklist to Ensure GenAI is Embedded
Used GenAI in idea proposal phase
Used GenAI in code development or debugging
Integrated at least 1 GenAI-based feature into the final app
Used GenAI for report or slide writing